## Sheet1
| Mon 09/05/22 - Sun 09/11/22 | Mon 09/12/22 - Sun 09/18/22 | Mon 09/19/22 - Sun 09/25/22 | Mon 09/26/22 - Sun 10/02/22 | Mon 10/03/22 - Sun 10/09/22 | Mon 10/10/22 - Sun 10/16/22 | Mon 10/17/22 - Sun 10/23/22 | Mon 10/24/22 - Sun 10/30/22 | Mon 10/31/22 - Sun 11/06/22 | Mon 11/07/22 - Sun 11/13/22 | Mon 11/14/22 - Sun 11/20/22 | Mon 11/21/22 - Sun 11/27/22 | Mon 11/28/22 - Sun 12/04/22 | Mon 12/05/22 - Sun 12/11/22
| Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
Nathaly (CS) | Week 3: Recall; Week 4: Preparation: ML Context, Article Reading, etc; Week 6: Project 1 Part 1: Recreate Research Article; Run Locally As Is with Real Dataset; Week 9: Finalize Part 1; Start Part 2; Week 10: Project 1 Part 2: Tune Algorithm Parameters/Test with Fake Dataset (dependent on hardware development state); Week 13: Project 1 Part 3: Integrate with Hardware (Stretch Goal); Week 15: Final Report
Anna (CS)
Siri (CS) | Week 3: Context
Esther (BioChem) | Week 6: Get familiar with Autodesk; Week 7: Researching and brainstorming how to automatically rotate images, continue to work on Autodesk if needed; Week 9: Implement idea to automatically rotate images, make improvements to the CAD model; Week 11: Test the updated Paradign model with the improvements; Week 12: Improve Paradigm further if needed, and research ways to fix image slide to the rotating plate; Week 13: Discuss and implement fixing image slide to rotating plate.; Week 14: Finalize CAD model improvements, and test if idea to fix image slide to rotating plate works
Raghav (BME) | Week 6: Get familiar with Autodesk; Week 7: Researching and brainstorming how to automatically rotate images, continue to work on Autodesk if needed; Week 9: Implement idea to automatically rotate images, make improvements to the CAD model; Week 11: Test the updated Paradign model with the improvements; Week 12: Improve Paradigm further if needed, and research ways to fix image slide to the rotating plate; Week 13: Discuss and implement fixing image slide to rotating plate.; Week 14: Finalize CAD model improvements, and test if idea to fix image slide to rotating plate works
Notices | Week 3: 5th: Schedule Check-In; Week 5: 19th: Schedule Check-In; Week 6: 30th: Project Plan Due; Week 7: 3rd: Schedule Check-In; Week 9: 17-18th: Fall Break; Week 13: 14th: Schedule Check-In; Week 16: 6th: Final Note Check
| 9th: Team Contract |  |  | 30th: Note Check | 7th: Midterm Evaluation | [8 empty] | 6th: Final Report
6th: Locker Cleanup (if)
7th: Final Evaluation
7th: Extra Credit (if)